## Info
INFORMATION | DETAILS
Project ID
Project Name | TWS Calendar Automation
Estimated Time-line (Hours) | 245
Estimated Time-line (Days) | 30.625
Planned Start Date | 2015-08-18
Planned End Date | 2015-09-28
Actual Start Date | 2015-08-18
Actual End Date | --

## Estimation
PHASES | COMMENTS & ASSUMPTIONS | HOURS | STATUS
RESEARCH & PLANNING |  | 8
Requirement Gathering/Analysis |  | 4 | completed
Project Planning |  | 4 | completed
SOLUTION DESIGN |  | 2
Wire-frame |  |  | in-progress
Requirement Specification |  |  | in-progress
ENVIRONMENT SETUP |  | 2
GIT/Eclipse/Maven/Spring configuration |  | 2 | started
FRONT END DEVELOPMENT |  | 5
Index Section | HTML + CSS template | 1
Calendar Jobs onload | combo box | 1
Holidays Input | file input (text file format) | 1
Calendar Year Selection | Date Input | 1
Input Validations |  | 1
Events and Overall Behaviors |  | 1
BACK END DEVELOPMENT |  | 204
Fetch Calendar Jobs | a. Read properties files b. Pass list to front end (to combo box) | 4
Input Validation and Processing | a. Validate Input b. Save holiday list in the server | 8
Calendar Jobs
PSF_BIL_CL_1ST_WD_WK (PSFBIL05) | Develop Rules Logic | 4
PSF_ACR_CL_WD1_CHK (PSFACR15) | Develop Rules Logic | 4
PSF_BIL_CL_WKD_TO_SAT_SKIP_MON (PSFBIL02) | Develop Rules Logic | 4
PSF_ACR_CL_BI_PIA_UNRD_CAL_18 (PSFACR14) | Develop Rules Logic | 4
PSF_BIL_CL_NON_1ST_WD_WK (PSFBIL03) | Develop Rules Logic | 4
PSF_ACR_CL_ADHOC_LOCKBOX (PSFACR08) | Develop Rules Logic | 4
PSF_ACR_CL_BI_NON_WD1_CHK (PSFACR13) | Develop Rules Logic | 4
PSF_ACR_CL_WEEKDAYS (PSFACR16) | Develop Rules Logic | 4
PSF_ACR_CL_DAILY (PSFACR17) | Develop Rules Logic | 4
PSF_ACR_CL_2PRI_CAL1 (PSFACR00) | Develop Rules Logic | 4
PSF_ACR_CL_2PRI_CAL24 (PSFACR02) | Develop Rules Logic | 4
PSF_ACR_CL_2PRI_CAL25 (PSFACR03) | Develop Rules Logic | 4
PSF_ACR_CL_2PRI_CAL6 (PSFACR04) | Develop Rules Logic | 4
PSF_ACR_CL_4PRI_CAL1 (PSFACR06) | Develop Rules Logic | 4
PSF_ACR_CL_2PRI_CAL10 (PSFACR01) | Develop Rules Logic | 8
PSF_ACR_CL_AR032UHC_10 (PSFACR10) | Develop Rules Logic | 8
PSF_ACR_CL_AR032UHC_01 (PSFACR09) | Develop Rules Logic | 8
PSF_ACR_CL_AUTO_MAINT_ZERO_BAL (PSFACR11) | Develop Rules Logic | 8
PSF_ACR_CL_2PRI_NON_WD1_BYPASS (PSFACR05) | Develop Rules Logic | 8
Calendar Rule and Holidays Mapping | a. Generate calendar year based on input b. Apply calendar rule based on job c. Apply holidays d. Save to Object | 32
Generate Calendar Output (Excel) | a. Fill out calendar months and days b. Mark dates result of the job rules c. Mark the holiday dates | 40
Unit Testing |  | 24
TESTING |  | 16
Internal Testing (Functional/Security)
User Acceptance Test (UAT)
GO LIVE |  | 8
Deployment Works
TOTAL |  | 245
|  | 30.625 | days

## Plan
ID | TASK | PRIORITY | HOURS | DEPENDENCIES | COMPLETION | START DATE(PLANNED) | FINISH DATE(PLANNED) | DAYS(PLANNED) | START DATE(ACTUAL) | FINISH DATE(ACTUAL) | DAYS(ACTUAL) | DAYS(DELAY) | REMARKS
1 | RESEARCH & PLANNING |  | 8 |  | 100% | 2015-08-18 | 2015-08-19 | 1 | 2015-08-18 | 2015-08-19 | 2 | 0
1.1 | Requirement Gathering/Analysis | [6 empty] | 0
1.1.1 | Create Project Analysis Document | Medium |  |  | 100% | 2015-08-18 | 2015-08-18 | 1 | 2015-08-18 | 2015-08-18 | 1 | 0
1.2 | Project Planning | [6 empty] | 0
1.2.1 | Create Project Plan Document | Medium |  |  | 100% | 2015-08-19 | 2015-08-19 | 1 | 2015-08-19 | 2015-08-19 | 1 | 0
2 | SOLUTION DESIGN |  | 2 |  | 14.06% | 2015-08-20 | 2015-08-20 | 0.25 | 2015-08-19
2.2 | Wire-frame | [6 empty] | 0
2.2.1 | Create Front End Wire-frame | Low |  |  | 0% |  |  | 0
2.2.2 | Create Back End Wire-frame | Low |  |  | 0% |  |  | 0
3 | ENVIRONMENT SETUP |  | 2 |  | 6.25% | 2015-08-20 | 2015-08-20 | 0.25
3.1 | GIT/Eclipse/Maven/Spring configuration | High |  |  | 50% |  |  | 0
4 | FRONT END DEVELOPMENT |  | 5 |  | 0% | 2015-08-20 | 2015-08-20 | 0.625
4.1 | Index Section | Low |  |  | 0% |  |  | 0
4.2 | Calendar Jobs onload | High |  |  | 0% |  |  | 0
4.3 | Holidays Input | High |  |  | 0% |  |  | 0
4.4 | Calendar Year Selection | High |  |  | 0% |  |  | 0
4.5 | Input Validations | Medium |  |  | 0% |  |  | 0
4.6 | Events and Overall Behaviors | Medium |  |  | 0% |  |  | 0
5 | BACK END DEVELOPMENT |  | 204 |  | 0% | 2015-08-21 | 2015-09-23 | 24
5.1 | Fetch Calendar Jobs | [6 empty] | 0
5.1 | Read properties files |  |  |  | 0% |  |  | 0
5.1 | Pass list to front end |  |  |  | 0% |  |  | 0
5.2 | Input Validation and Processing | [6 empty] | 0
5.2 | Validate Input |  |  |  | 0% |  |  | 0
5.2 | Save holiday list in the server |  |  |  | 0% |  |  | 0
5.3 | PSF_BIL_CL_1ST_WD_WK (PSFBIL05) | [6 empty] | 0
5.3 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.4 | PSF_ACR_CL_WD1_CHK (PSFACR15) | [6 empty] | 0
5.4 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.5 | PSF_BIL_CL_WKD_TO_SAT_SKIP_MON (PSFBIL02) | [6 empty] | 0
5.5 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.6 | PSF_ACR_CL_BI_PIA_UNRD_CAL_18 (PSFACR14) | [6 empty] | 0
5.6 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.7 | PSF_BIL_CL_NON_1ST_WD_WK (PSFBIL03) | [6 empty] | 0
5.7 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.8 | PSF_ACR_CL_ADHOC_LOCKBOX (PSFACR08) | [6 empty] | 0
5.8.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.9 | PSF_ACR_CL_BI_NON_WD1_CHK (PSFACR13) | [6 empty] | 0
5.9.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.10 | PSF_ACR_CL_WEEKDAYS (PSFACR16) | [6 empty] | 0
5.10.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.11 | PSF_ACR_CL_DAILY (PSFACR17) | [6 empty] | 0
5.11.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.12 | PSF_ACR_CL_2PRI_CAL1 (PSFACR00) | [6 empty] | 0
5.12.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.13 | PSF_ACR_CL_2PRI_CAL24 (PSFACR02) | [6 empty] | 0
5.13.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.14 | PSF_ACR_CL_2PRI_CAL25 (PSFACR03) | [6 empty] | 0
5.14.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.15 | PSF_ACR_CL_2PRI_CAL6 (PSFACR04) | [6 empty] | 0
5.15.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.16 | PSF_ACR_CL_4PRI_CAL1 (PSFACR06) | [6 empty] | 0
5.16.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.17 | PSF_ACR_CL_2PRI_CAL10 (PSFACR01) | [6 empty] | 0
5.17.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.18 | PSF_ACR_CL_AR032UHC_10 (PSFACR10) | [6 empty] | 0
5.18.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.19 | PSF_ACR_CL_AR032UHC_01 (PSFACR09) | [6 empty] | 0
5.19.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.20 | PSF_ACR_CL_AUTO_MAINT_ZERO_BAL (PSFACR11) | [6 empty] | 0
5.20.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.21 | PSF_ACR_CL_2PRI_NON_WD1_BYPASS (PSFACR05) | [6 empty] | 0
5.21.1 | Develop Rules Logic |  |  |  | 0% |  |  | 0
5.22 | Calendar Rule and Holidays Mapping | [6 empty] | 0
5.22.1 | Generate calendar year based on input |  |  |  | 0% |  |  | 0
5.22.2 | Apply calendar rule based on job |  |  |  | 0% |  |  | 0
5.22.3 | Apply holidays |  |  |  | 0% |  |  | 0
5.22.4 | Save to Object |  |  |  | 0% |  |  | 0
5.23 | Generate Calendar Output (Excel) | [6 empty] | 0
5.23.1 | Fill out calendar months and days |  |  |  | 0% |  |  | 0
5.23.2 | Mark dates result of the job rules |  |  |  | 0% |  |  | 0
5.23.3 | Mark the holiday dates" |  |  |  | 0% |  |  | 0
5.24 | Unit Testing | [6 empty] | 0
5.24.1 | junit |  |  |  | 0% |  |  | 0
6 | TESTING |  | 16 |  | 0% | 2015-09-24 | 2015-09-26 | 2
6.1 | Internal Testing (Functional/Security) | [6 empty] | 0
6.1.1 | Creation of Test Scripts |  |  |  | 0% |  |  | 0
6.1.2 | Functional Testing |  |  |  | 0% |  |  | 0
7 | DOCUMENTATION | [6 empty] | 1
7.1 | User Training Manual |  |  |  | 0% |  |  | 0
7.2 | Installation Steps
8 | GO LIVE |  |  |  | 0% |  |  | 1
8.1 | Upload Files |  |  |  | 0% |  |  | 0
8.2 | Misc. Setting Works |  |  |  | 0% |  |  | 0
| TOTAL | [6 empty] | 30.125
Formulas:
DAYS(ACTUAL) = NETWORKDAYS([START DATE(ACTUAL)],[FINISH DATE(ACTUAL)])
DAYS(DELAY) = NETWORKDAYS([FINISH DATE(PLANNED)],[FINISH DATE(ACTUAL)])-1
DAYS(PLANNED) = NETWORKDAYS([START DATE(PLANNED)],[FINISH DATE(PLANNED)])

## Guidelines
PHASES | EFFORT
RESEARCH & PLANNING | 5%
SOLUTION DESIGN | 5%
DEV ENVIRONMENT SETUP | 5%
FRONT END DEVELOPMENT | 10%
BACK END DEVELOPMENT | 60%
TESTING | 10%
GO LIVE | 5%
TOTAL | 100%